## Slide 1: INTT Status and Schedule
Itaru Nakagawa
RIKEN/RBRC

## Slide 2: Number of INTT Layers
Decision was made to be 2 layers in the sPHENIX EC meeting on Wednesday following discussion in the sPHENIX collaboration meeting at FSU.
The radius of 2 layers to be optimized soon.
Layer | Radius [cm] | # of Ladders
1 | 6 | 20
2 | 8 | 26
3 | 10 | 32
4 | 12 | 38
Total |  | 116
Layer | Radius [cm] | # of Ladders
2 | 8 | 26
3 | 10 | 32
Total |  | 58

## Slide 3
2016 |  | 2017 |  |  |  | 2018 |  |  |  | 2019 | 
R&D Status and Schedule Update
Pre-production
Final Design Review
Ladder L123 Prototype-I
Bus Extender
Prototype-0
Prototype-I
Beam test II
Beam test I
Ladder L123 Pre-Production
Ladder L0 Prototype-I
L0 Prototype-II?
Pre-Production
Prototype-II
Middle of May

## Slide 4: Towards beam test
Silicon
  8 sets preproduction versions are delivered in Feb. 2018.
HDI
  Preproduction version to be delivered by the end of Feb.
Stave
  Preproduction version is to be procured.
Bus Extender
  Preproduction manufacture is in progress. Delivery in end of Jan. To be tested in Feb. – March.
Conversion Cable
  Procurement paper works is in progress. To be delivered by the end of March.
Assembly in March
Chain test in March - April

## Slide 5: New Collaboration
Discussion with Prof. Chia-Ming Kuo from NCU/Taiwan for the collaboration in INTT production.
Abundant experiences in silicon detector assembly/testing.
Assembly work of silicon shower counters for CMS is ongoing.
Infrastructure of the silicon laboratory in Taiwan
Nov.13th, 2018
Possible collaboration in QA, testing, assembly, etc in the production phase.

## Slide 7: Towards Production
Silicon
  Hamamatsu (Japan)
  90% Fraction of actual use is under procurement in JFY2018
FPHX Chip
  Production (MOSIS) -> Tested (Fermi Lab) completed in JFY2017
  We have 200% chips available of actual use.
HDI
  Hayashi REPIC (Japan)
  Preproduction design is now under procurement
Stave
  ASUKA (Japan)
    Requested a quote for the preproduction design
  LBNL (USA)

## Slide 8: Assembly Location
BNL
  Facility
  Available Technicians, but expensive ($0.3M/year x 2 years)
Fermi Lab
  Facility
  Available Technicians, less expensive than BNL?
Japan
  Facility in REPIC
  Students
Perdue
  Facility
  Students, Post-doc, technicians? depends on funding request?
Taiwan
  Facility
  Funding?
  Students, a few technicians?

## Slide 9: backup

## Slide 12: Schedule in Details